## Sheet1
Cybersecurity Implementation Action Plan (Matrix)
Ref No. | Task | Year to be completed | Responsible Owner | Board Role | Budget/Source | Key Dates | Status | Next Steps

## Sheet2
Cybersecurity Implementation Guideline Action Plan (Matrix)
Task No. | Task | Method of implementation | Responsible party | Stakeholder | Budget/Source | Time frame for completion
Creating information security policy for compliance with the requirement of National Information Technology Development Agency Data Privacy/Protection Guideline 2020
1.1 | Activate organizational processes to compliy with NITDA Nigeria Data Protection Regulation Guidelines 2020 | Appointment of an Independent Data Protection Compliance Organization (DPCO) and Data Protection Officer (DPO) to carry our independent assessment of OGFZA's NDPR compliance actitvities | ICT Department | Management | N2,500,000 | 2021-03-01
Conduct assessment of the existing organisational environment and determine the existing security controls and what has not been implementation as required by NITDA
1.2 | DPCO to conduct assessment of the existing environment | DPCO to conduct a comprehensive assessment of the current security controls and determine where we are, and where ought to be | DPCO | DPO | N1,000,000 | 2021-04-01
1.3 | Determine organizational assets and prioritize | Take inventory of all organizational assets and assign priority according to the protection required | ICT Department | Management | N500,000 | 2021-05-01
Develop Information Security Policies to guide stakeholders and employees within the organization
1.4 | Develop IT policies | Develop Computer use polices, email use policy, Acceptable use policy, etc | ICT Department | Management | N1,200,000 | 2021-06-01
Determination of Risk Management and Communications System between Stakeholders
1.5 | Implement a system for reporting and responding to security incidents | Implement a cloud-based reporting system lodging incident report | ICT Department | Management | N2,000.000 | 2021-07-01
Implementation of Security Controls as required by NIST and CIS
1.6 | Implement security controls | Implement all the necessary controls according to organization specific needs. This involved procuring all needed security solutions | ICT Department | Management | N15,000,000 | 2021-08-01
Implementation of Awareness System and Cybersecurity Education for Employees and Stakeholder
1.7 | Create a cybersecurity awareness | Launch a series of cybersecurity awareness program to educate employees and stakeholders on roles expected of them | ICT Department | Management | N1,000.000 | 2021-09-08
1.8 | Create a cybersecurity culture | Stakeholders engagement is needed here to create a cybersecurity | ICT Department | Management | N2,000,000 | 2021-10-01